## Overview
Field | Value
Project Name | EduFlow AI
Type | Intelligent Study Planning Platform
Frontend | React
Backend | ASP.NET Core 8
Database | SQL Server 2022, Mongo DB
Hosting | Azure
Status | R&D Phase
Duration | 3 Months

## Features
EduFlow AI
Features | Phases | Status
Authentication | Phase 1 | Planned
User Profile | Phase 1 | Planned
Goal Management | Phase 1 | Planned
Task Management | Phase 1 | Planned
Planner Engine V1 - V4 | Phase 1 | Research
Schedule Generator | Phase 1 | Research
Dashboard | Phase 1 | Research
Calender | Phase 1 | Planned
Progress Tracking | Phase 1 | Planned
Rescheduling | Phase 2 | Not Started
AI RoadMap | Phase 2 | Not Started
AI Recommendations | Phase 2 | Not Started
Google Calender Sync | Phase 2 | Not Started

## Open Questions
Doubts
Question | Priority
How should planner calculate priority? | High
Should estimated hours be mandatory? | High
Which scheduling algorithm to use? | High
How should missed tasks be handled? | High
How should AI estimate study effort? | Medium
How should Google Calendar integration work? | Low

## Color Theme
Purpose | Color | Hex | Status | Color | Element | Color | Hex | Primary Heading : #4F46E5
Primary | Indigo | #4F46E5 | Completed | #22C55E | Cover Title | Indigo | #4F46E5 | Sub Heading : #06B6D4
Secondary | Cyan | #06B6D4 | In Progress | #06B6D4 | Main Headings (H1) | Indigo | #4F46E5 | Body Text : #0F172A
Success | Green | #22C55E | Research | #F59E0B | Sub Headings (H2) | Cyan | #06B6D4 | Table Header : #4F46E5
Warning | Amber | #F59E0B | Not Started | Light Gray | Normal Text | Dark Slate | #0F172A | Table Border : #CBD5E1
Background | Light Gray | #F8FAFC | Blocked | Red | Table Headers | Indigo | #4F46E5 | Future Enhancements : #F59E0B
Text | Dark Slate | #0F172A |  |  | Table Header Text | White | #FFFFFF | Background : #FFFFFF
[5 empty] | Table Borders | Gray | #CBD5E1
[5 empty] | Notes / Future Enhancements | Amber | #F59E0B
[5 empty] | Page Background | White | #FFFFFF

## EduFlow TimeLine
EduFlow AI TimeLine
EduFlow AI Phase 1 TimeLine
S.No | Task | Phase | Start Date | End Date | Status | Comments | Total Tasks | 16
1 | Creating Functional Requirements for the Project | Requirement Phase | 2026-06-16 | 2026-06-19 | Completed | The Function Requirement is been documented for the phase 1 only | Completed | 9
2 | Rough Sketching of the Project Workflow | Requirement Phase | 2026-06-27 | 2026-06-27 | Completed |  | In Progress | 2
3 | Database Structure Design | Database Design | 2026-06-21 | 2026-06-22 | Completed |  | Planned | 0
4 | UI / UX Design using Google Stitch and Figma | Designing Phase | 2026-07-02 | 2026-07-09 | In Progress |  | Completion % | 53.33%
5 | DB setup | Designing Phase | 2026-07-10 | 2026-07-10 | Completed | s
6 | Frontend Project Setup (React + Routing) | Frontend Development | 2026-07-10 | 2026-07-10 | Completed
7 | Authentication Screens (Login, Register, Forgot Password) | Frontend Development | 2026-07-11 | 2026-07-12 | Completed
8 | Dashboard, Goals, Tasks and Analytics UI | Frontend Development | 2026-07-13 | 2026-07-16 | In Progress
9 | Profile Management and Calendar View UI | Frontend Development | 2026-07-17 | 2026-07-19 | Completed
10 | Backend Project Setup (.NET Core 10, Architecture) | Backend Development | 2026-07-12 | 2026-07-12 | Completed
11 | Authentication APIs (Login, Register, Forgot Password) | Backend Development | 2026-07-20 | 2026-07-20 | Completed
12 | Goal Management, Task Management and User Profile APIs | Backend Development | 2026-07-21 | 2026-07-22
13 | Planner Engine V1 and Schedule Generation | Core Development | 2026-07-23 | 2026-07-31
14 | Dashboard Integration and Calendar Integration | Integration Phase | 2026-08-01 | 2026-08-05
15 | AI - Implementation of EduFlow AI and integration | AI Phase | 2026-08-06 | 2026-08-10
16 | Testing and Bug Fixing | Testing Phase | 2026-08-10 | 2026-08-11